## Sheet1
Legend: | Group 5 |  | (3 Hours Each)
Completed | Questions | Assigned to | Tasks | Completed | Planned Completion Date | Completed by | Bottleneck notes | Ideas
In Progress | Do disaster loans have a significant effect to mitigate unemployment? | Group | Found datasets | 2022-05-10 | 2022-05-10 | Group |  | Nick's idea for dashboard gauge showing loans requested vs awarded
Incomplete Bottleneck |  | Ryan | ETL - Unemployment | 2022-05-12 | 2022-05-12 | Ryan
|  | Chris | ETL - SMP 500 | 2022-05-11 | 2022-05-11 | Chris
|  | Jake | ETL - Census pre 2013 | 2022-05-11 | 2022-05-11 | Jake
|  | Jake | ETL - Census post 2013 |  | 2022-05-13
|  | Jake | ETL - Census post 2013 (2) (it's hard) |  | 2022-05-16
|  | Nick | Disaster Data API | 2022-05-10 | 2022-05-10 | Nick
|  | Mikhaela | ETL - Disaster Data | 2022-05-11 | 2022-05-11 | Mikhaela
|  | Jake | ETL - Merge tables |  | 2022-05-16
|  | Jake | ETL - Integrate with producer |  | 2022-05-16 |  | This and above ETL must be completed for ML steps
|  | Jake | Debug combined producer/ETL |  | 2022-05-16
|  | Everyone | ETL Report draft |  | 2022-05-17
|  | Ryan | ERD | 2022-05-10 | 2022-05-10 | Ryan
|  | Jake | ETL Report finalized |  | 2022-05-17
|  | Mikhaela | Create containers, datafactory, SQL database | 2022-05-10 | 2022-05-10 | Mikhaela
|  | Chris | Kafka Producer Prototype | 2022-05-11 | 2022-05-11 | Chris | All prototypes need to be done week 1
|  | Chris | Kafka Consumer Prototype | 2022-05-11 | 2022-05-11 | Chris | All prototypes need to be done week 1
|  | Nick | Visuals napkin drawing draft | 2022-05-11 | 2022-05-11 | Nick
|  | Jake | Visuals napkin drawing feedback | 2022-05-11 | 2022-05-11 | Jake
|  | Mikhaela | Visuals napkin drawing revision | 2022-05-11 | 2022-05-11 | Mikhaela
|  | Chris | Writing to SQL prototype | 2022-05-12 | 2022-05-12 | Chris | All prototypes need to be done week 1
|  | Chris | Datafactory Pipeline | 2022-05-12 | 2022-05-12 | Chris | All prototypes need to be done week 1
|  | Mikhaela | Machine Learning Model Prototype | 2022-05-11 | 2022-05-11 | Mikhaela | All prototypes need to be done week 1
|  | Chris | Export Prototype Machine Learning Model | 2022-05-11 | 2022-05-11 | Chris | All prototypes need to be done week 1
|  | Mikhaela | Create PowerBi environment | 2022-05-12 | 2022-05-13 |  | All prototypes need to be done week 1
|  | Mikhaela | connect to powerbi |  | 2022-05-13 |  | All prototypes need to be done week 1
|  | Jake | Cloud Diagram | 2022-05-12 | 2022-05-12 | Jake
|  | Ryan | Finalize SQL database format |  | 2022-05-16 |  | Needs to be done for PowerBI
|  | Mikhaela & everyone else | Dash Napkin drawing draft |  | 2022-05-17 |  | Needs to be done for PowerBI
|  | Group | Dash Napkin drawing feedback |  | 2022-05-17 |  | Needs to be done for PowerBI
|  | Mikhaela & everyone else | Dash Napkin drawing revision |  | 2022-05-17
|  | Chris | Finalize kafka producer |  | 2022-05-17
|  | Chris | Finalize kafka consumer |  | 2022-05-17
|  | Chris, Ryan | ML Model - Tuning |  | 2022-05-18
|  | Chris, Ryan | ML Model - Tuning (2) |  | 2022-05-18
|  | Chris, Ryan | ML Model - Test variants |  | 2022-05-18
|  | Chris | ML Model - Test different data |  | 2022-05-18
|  | Chris | Iterate tuning if necessary |  | 2022-05-19
|  | Jake | Revise ETL if necessary |  | 2022-05-19
|  | Group | Finalize ML |  | 2022-05-20 |  | Needs to be done for presentation/final report
|  | Nick | Draft visuals 1 |  | 2022-05-22
|  | Nick | Draft visuals 2 |  | 2022-05-22
|  | Nick | Finalize visuals 1 |  | 2022-05-23
|  | Nick | Finalize visuals 2 |  | 2022-05-23
|  | Group | Draft PowerBI report |  | 2022-05-24
|  | Group | Finalize powerBI report |  | 2022-05-24
|  | Group | Draft report intro and conclusion |  | 2022-05-25
|  | Group | Draft body of report |  | 2022-05-25
|  | Group | Draft body of report (2) |  | 2022-05-25
|  | Group | Finalize report |  | 2022-05-25
|  | Group | Draft Presentation |  | 2022-05-26
|  | Group | Draft Presentation (2) |  | 2022-05-26
|  | Group | Finalize Presentation |  | 2022-05-26
|  | Group | Practice Presentation |  | 2022-05-26
|  | Mikhaela | Github README |  | 2022-05-26
Totals of assigned projects
Chris = 13
Jake = 10
Mikhaela = 7
Nick = 6
Ryan = 6
Group = 16